## 1 - Capture Form (hidden)
Risk and Issue Capture Form
Local ID | Title
Raised by | Date raised | dd/mm/yy | Workstream L1 | Probability % | 0 | Severity Score | 0
Risk Contact / Reviewer | Target Resolution Date |  | Workstream L2 | Cost | NO IMPACT
Owner | Trigger Date |  | Other Areas Impacted | Quality | NO IMPACT | Wkstrm/ Proj Severity | Low
Response Type | External_Coms |  | Stage | Time | NO IMPACT
Description |  |  | Impact Description
Mitigation actions / Resolution |  |  | Monitoring Actions
Fallback / Contingency |  |  | Impact Explanation
[8 empty] | Yes | P1R1 | CDA / Requriemetns
[8 empty] | No | P1R2 | CDA / Design Authority
[9 empty] | P2R1 | CDA / Value Management
[9 empty] | P2R2 | CDA / Business Process Change
[9 empty] | P3 | CDA / Service Development
[9 empty] | All Development Stages | CDA / Clinical Group
CDA / Assurance
Delivery / P1R1
Delivery / P1R2
Delivery / P2R1
Delivery / P3
Delivery / Deployment
Service Management
Mobilisation
Commercial
Finance
Quality
PMO
Fujitsu
LSPM

## 2 - Capture Form Guide (hidden)
Risk and Issue Capture Form
The purpose of the capture form is to ensure that before the risk/issue is entered into the local workstream log: - The basic information has been captured - it is intended to focus the raiser on capturing the right information. - That the High Level Assessment (HLA) of the impact is reasonably accurate - assists in prioritising the risk or issue. - An authorised person (the workstream risk/issue contact, PM or the PMO) has reviewed the information to ensure quality, clarity, suitability, remove duplications and ensure the correct owner has been allocated.
Local ID | The Workstream Risk/Issue Contact will provide this. | Title | A brief but informative title to explain the risk / issue. Short & concise but pertinent & relevant.
Raised by | Enter the name of person raising the risk / issue. | Date raised | dd/mm/yy. Enter the date when the risk / issue was raised & received by the appropriate Workstream Risk/Issue Contact. | Workstream L1 | The workstream / project area where the owner belongs. 1st level sort - i.e. Delivery or Finance areas (DEL & FIN in drop-down list respectively). | Probability | Using scaling tables, the risk is accessed in terms of it actually occurring i.e. there is around 60% chance of it happening. If a risk has a probability of more than 80% then it is an issue and the probability is set to 100. | Severity Score | Automated field. Calculated from Probability, Cost, Quality & Time scores. Calculated field - used to determine escalation to Programme Risk Management Team. If >50 then the risk / issue must be passed to the Risk Management Team to be logged in Programme Database.
Risk Contact / Reviewer | Authorised Workstream Risk/Issue Contact for the Programme area. | Target Resolution Date | dd/mm/yy. Date by which mitigating actions need to be resolved / in actions to avoid the risk/ to resolve the issue as planned. | Workstream L2 | The workstream / project area where the owner belongs. 2nd level = pick list for each workstreams areas. | Cost | Cost of Impact If risk occurs. Use scaling tables on sheet 5.
Owner | This is the person who is primarily responsible for the R/I and will manage the mitigating actions (others may be the owners of various actions). | Trigger Date | Event / date Impact will be triggered, or be come unavoidable. When this date is hit the Risk will be come an issue, and the probability should be raised to 100% | Other Areas Impacted | Please use this field to indicate any other areas / workstreams, which could be / are affected by this risk / issue. | Quality | Impact on quality if risk occurs. Use scaling tables on sheet 5. | Wkstrm/ Proj Severity | Automated. Calculated from NPfIT score - for use by the Project area. High = 50 + Med = 20 to 50 High = below 20
Response Type | Which way are we attempting to handle the Risk/issue? Chose category from the drop-down list. | External_Coms | External Communication. Can the Risk/Issue be communicated to/discussed with with NPfIT or 3rd Parties? - 'Yes'. Will be reported if/when felt appropriate. - 'Yes - Inform Auth'. It is important that this is shared with/reported to NPfIT. - 'No' - Sensitive'. The risk/issue is too sensitive & should not be reported or discussed externally without careful consideration. This will indicate to the PMO RMT to check before including in any external reporting such as the monthly NPfIT reviews. | Stage | The stage in the LSP Programme that the risk / issue impacts. (Chose from drop-down list) | Time | Time delay if risk occurs. Use scaling tables on sheet 5.
Description | This must describe what the risk or issue is. A statement of fact is not adequate. i.e. 'There is a risk that …' or 'The issue is that ...' |  |  | Impact Description | A brief explanation of the impact should the risk occur, i.e. “If this risk occurs ...” If an issue, describe the impact it is having now. Specify the point at which the impact will be triggered (relating to the 'Trigger Date').
Mitigation actions / Resolution | The formal action plan which is to be undertaken to prevent the risk from occurring/to resolve the issue Must include any high-level tasks or activities to be performed by whom and by what date. Note: Detailed /specific actions will be noted with dates and owners in the 'Open Actions' field. |  |  | Monitoring Actions | How the risk / issue is to be monitored? i.e. through weekly reports, monthly project board meetings etc
Fallback / Contingency | What is plans / actions are in place if the risk was to occur? |  |  | Impact Explanation | Briefly explain how the scores have been achieved to validate Cost, Quality and Time values i.e. = 1 month delay due to ……. Penalties incurred cost £ x (estimate) Extra resource time / or equipment etc = £ …. Quality reduced as …. Note: this will be updated & clarifies when the full Impact Assessment is undertaken.
[10 empty] | Yes | P1R1 | CDA / Requirements
[10 empty] | No | P1R2 | CDA / Design Authority
[11 empty] | P2R1 | CDA / Value Management
[11 empty] | P2R2 | CDA / Business Process Change
[11 empty] | P3 | CDA / Service Development
[11 empty] | All Development Stages | CDA / Clinical Group
CDA / Assurance
Delivery / P1R1
Delivery / P1R2
Delivery / P2R1
Delivery / P3
Delivery / Deployment
Service Management
Mobilisation
Commercial
Finance
Quality
PMO
Fujitsu
LSPM

## Cover Page
Risk and Issue Log Created by: XXXXXXXXXXXXX Creation date: XX/XX/XXXX

## Reference Table
Field Name | Descripcion
Entry No | Unique number to identify risk and link it to the defined project.
Risk/Issue | Automatic field. Identify if it is a risk or an issue.
Program Level Impact? | Automatic field. Impact Level
Programme Severity | Automatic field. Severity
Status | Status of issue
Raised By | Resource who identified risk/issue
Date raised | Date in which risk/issue was updated on excel sheet
Owner | Resource who is repsonsable for doing the follow up and mitigate risk/issue
Module | Module
Other areas impacted | Areas in which risk might impact
Title | Title
Description | Descripcion
Category | Category
Impact Description | A clear description of the impact the risk/issue has on the current project
Trigger Date | Date in which risk/issue will began to be looked at.
Cause of Risk / Issue | Cause
Mitigating Action / Resolution Plan | Mitigation plan
Target Date | Target date that risk/issue should be mitigated and solved.
Progress / Review Notes | Progress / Review notes
Escalate to Program (Y/N)
Actions To Do
Date of last update
Probability %
Cost Impact
Quality / Service Impact
Time Impact
Score | Automatic field. Puntaje con el que se califica al riesgo
Module Severity | Automatic field. Severidad en el Módulo
Status | Projects | Category | Escalate to Program
1 - Open | Proteci | Management | Yes
2 - Assigned |  | Resources | No
3 - Closed |  | Schedule
Technical
3rd Party (Outsource)
.
.

## Scaling Table
Program - Probability & Impact Scaling Tables
Probability of Occurrence | Description | % Probability
Issue | Risk has been triggered | 100 %
VH - Very High | Extremely likely to happen | 70 - 80%
H – High Probability | More Likely to happen than not | 50 - 69%
M – Medium Probability | Fairly Likely to happen | 20 - 49%
L – Low Probability | Low, but not impossible | 5 -19%
VL – Very Low | Unlikely to occur | <5%
Impact On Time | Description of Likely Delay | Scoring
VH – Very High | Major delay to all key program milestone ≥1month | 10
H – High Impact | Delay to program milestone of >1-3 weeks | 6
M – Medium Impact | Delay to program milestone of up to 1 week | 3
L – Low Impact | Delays to project tasks, which does not impact any milestones | 2
VL – Very Low | Delays wholly contained within projects with no impact on milestones | 1
Impact On Cost | Cost of Likely Impact | Scoring
VH – Very High | Costs above | 10
H – High Impact | Costs between | 6
M – Medium Impact | Costs between | 3
L – Low Impact | Costs between | 2
VL – Very Low | Costs of < | 1
Impact On Quality/Service | Description of Likely Impact in Terms of Quality and/or Service | Scoring
H – High | Product service and quality not acceptable | 10
M – Medium Impact | Product service and quality compromised | 6
L – Low Impact | Product service and quality containable | 3

## Risk & Issue Log
Entry No | Risk/Issue | Program Level Impact? | Programme Severity | Status | Raised By | Date raised | Owner | Projects | Other areas impacted | Title | Description | Category | Impact Description | Trigger Date | Cause of Risk / Issue | Mitigating Action / Resolution Plan | Target Date | Progress / Review Notes | Escalate to Program (Y/N) | Actions To Do | Date of last update | Probability % | Cost Impact | Quality / Service Impact | Time Impact | Score | Project Severity
1 | Risk | Yes | H | 2 - Assigned | Karina Blanco | 2014-10-04 | Karina Blanco | Inmobiliaria | MGM | Experiencia | Falta de experiencia del equipo en el negocio | 3rd Party (Outsource) | Retraso en el comienzo de desarrollo de la herramiento | 2014-10-20 | Mala eleccion del equipo | Planificar cursos de capacitacion e invitar al PO a participar de actividades con el equipo |  |  | Yes | Contratar un agente especializado en el negocio | 2014-10-04 | 75 | H | H | M | 56.25 | High
2 | Risk | Yes | H | 2 - Assigned | Karina Blanco | 2014-10-05 | Karina Blanco | Inmobiliaria | MGM | Fondos | Falta de recursos financieros | 3rd Party (Outsource) | Cancelacion del proyecto | 2014-10-25 | Mala planificacion | Realizar planificacion de admin de fondos eliminando gastos innecesarios |  |  | Yes | Renegociar con el cliente condiciones del contrato | 2014-10-04 | 75 | H | H | VH | 82.5 | High
3 | Risk | No | VL | [22 empty] | 0 | Low
4 | Risk | No | VL | [22 empty] | 0 | Low
5 | Risk | No | VL | [22 empty] | 0 | Low
6 | Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
| Risk | No | VL | [22 empty] | 0 | Low
Note on G1: diego.varela: dd/mm/yyyy
Note on O1: diego.varela: dd/mm/yyyy
Note on R1: diego.varela: dd/mm/yyyy
Note on V1: diego.varela: dd/mm/yyyy